## moveit
MoveIt
Backend Node and Mongo
Name | Person | Status | Date
Proposal submit project pull request | Ashley Schweikhard | Done | 2022-07-01
Build out backend repo |  |  | 2022-06-30
initial commit with boiler plate setup backend: DB, MODEL, CONNECTION, INDEX, SCHEMA |  |  | 2022-06-30
Seed DB for USER model |  |  | 2022-07-01
Plan User Model queries and requests on router
Explore top 50 exercise model to make/take video of Syd. |  |  | 2022-07-01
Build top 50 exercise DB model for search option/filter |  |  | 2022-07-02
Seed top50 exc. to DB
Plan top5 exc. DB queries and requests on router
Test routes w/HTTP extension or Postman for main get requests
Test routes for post
Test routes for put
test routes for Delete
2022-06-30 to 2022-07-02
FrontEnd React Components
Name | Person | Status | Date
Decide on API to use: ExRx or Exercise DB |  | Working on it | 2022-07-01
Make dev free account ExRx API |  |  | 2022-07-01
Build out frontend repo
create react app
Establish installs: react router, axios
App/main file: structure planning
Establish components: home, loginform, signupform, editaccountform
Est. comp.: exercise card/search result(on click), search results, search bar
Est. comp.: search results filter buttons: by joint, by muscle group, by name
Est comp.
explore pagination for search results
establish figure out google auth login vs. passport
Est. comp.: login/auth modal
Est. comp: HEP bar/window, folder of HEPs, button: create HEP folder
Est. comp: Exercise library saved favorites (all)
Print pdf engine based on view/webpage
Edit account component: make buttons for edit and delete account w/modal for checking if user wants to make the change
2022-07-01
React Pages/Routes
Name | Person | Status | Date
Home/root/login page
modal to signup or modal to login/auth
User homepage
User Account
About Site Page/training platform
User Ex. Fav. Library + HEP
User Ex. Card View to print
User HEP view to print
Stretch goals/features
Name | Person | Status | Date
Add filter button for favorited items/exercise cards in user library
Drag and drop ex. cards into HEP window to create folder of custom HEP.
explore mobile styling, react native
STYLING
Name | Person | Status | Date
How to style?
What is Redux?
Bootstrap or No?
Grid or Col and rows, choose
Media queries for screen responsivity
Mobile version would require what?
Is React Native possible at the end? What will it take?
Routes and Query Requests
Name | Person | Status | Date
GET: Home
GET: SignupForm
GET User homepage
GET user Account page
GET about page
GET user library
GET user selected exc. card
GET user selected HEP folder
POST new account
POST new exercise/custom card in user library
POST new HEP folder
PUT edit HEP folder
PUT edit exercise card
DELETE exc. card from user library
DELETE HEP folder from user library